## Sourcing (Ph1)
|  | Appendix 3 | Contract Sourcing & Planning : breakdown of phase1 activities as per RACI model
Key: Responsibility person delivering the task. Accountability person with overall authority. Consulted persons who need to be actively engaged. Informed persons who need to be kept in the loop.
Order | Code | Key activity | Activity description | Responsibility | Accountability | Consulted | Informed
1 | 1a | Defining the approach to Contract & SRM | Agreeing the relative strategic importance of the required items to customer operations including the risks of disruption to supply, and consequently the nature, duration and key elements of the required contract(s) & SRM including dispute resolution. | HBS Procurement Category Lead | Head of Procurement | HBS Procurement National CFS Governance Group | HBS Procurement National CFS Governance Group
2 | 1b | Defining SL's, KPI's, measures & escalation | Balancing cost and required service levels. Setting out the appropriate KPI's measures and metrics, and the means of capturing the required data to measure supplier performance. Identifying trigger points for dispute escalation or positive recognition. | HBS Procurement Category Lead | Head of Procurement | HBS Procurement National CFS Governance Group | HBS Procurement National CFS Governance Group
3 | 1c | Defining compliane & savings measures | Clarifying what is meant by "compliance" in the context of the contract(s) and linking this where applicable to payment and savings measures. Confirming savings methodology. | HBS Procurement Category Lead | Head of Procurement | HBS Procurement National CFS Governance Group | HBS Procurement National CFS Governance Group
4
5
6
7
8

## Contract formation (Ph2)
|  | Appendix 1 | Contract formation & mobilisation: breakdown of phase2 activities as per RACI model
Key: Responsibility person delivering the task. Accountability person with overall authority. Consulted persons who need to be actively engaged. Informed persons who need to be kept in the loop.
Order | Code | Key activity | Activity description | Responsibility | Accountability | Consulted | Informed
1 | 2a | Finalise Contract Documents/ Schedules | Completing the detailed CHO specific schedules/ annexes to (standard) contracts with CHO involvement if applicable. Pre-contract meetings, addition of database input by companies | HBS Procurement Category Lead | Head of Procurement | CHO CFS Coordinator CHO CFS Management Group | CHO CFS Coordinator CHO CFS Management Group HBS Procurement
2 | 2b | Facilitating transition to new arrangements | All internal and external communications, system changes, and activities required to move from an existing incumbent supplier(s) to the new arrangements | CHO CFS Coordinator with HBS Procurement Category Lead | Head of Service Head of Procurement | CHO CFS Management Group Communications HBS Finance
3 | 2c | Provision of CM Guidance & Training to customers CBUG | Development and dissemination of Contract Management “handover pack” to customers containing a mix of general and specific guidance on how to manage “the contract” in plain English. May be supplemented by training and/or information sessions | HBS Procurement Category Lead | Head of Procurement | CHO CFS Management Group Communications | Head of Service CHO CFS Coordinator CHO CFS Management Group
4
5
6
7
8

## Contract operation (Ph3)
|  | Appendix 1 | Contract operation: breakdown of phase 3 activities as per RACI model
Key: Responsibility person delivering the task. Accountability person with overall authority. Consulted persons who need to be actively engaged. Informed persons who need to be kept in the loop.
Order | Code | Key Activity | Activity description | Responsibility | Accountability | Consulted | Informed
1 | 3a | Uploading contracts on CHO systems | Activities required to upload new contract to CHO finance/payment system so that ordering and payment can be made per contract and spend data captured. Some contracts have products which will need to be communicated to each CHO to upload locally, as the product is a purchase only ie it is not uploaded to PASS system | Procurement Lead/ National finance | Head of Procurement/Chief Financial officer | National CFS Governance Group Head of Primary Care | National CFS Governance Group Head of Primary Care National CFS Coordinator
2 | 3b | Ordering, Expediting & Receipting | CHO status quo or “Business as Usual” activity to create, authorise and transmit purchase orders to suppliers for requirement fulfilment. “Order chasing” if required and receipting. On foot of contract management agreement, complete operational process flows, SOP, agreement for same through governance channels | CHO CFS Management Group | Chief Officer | National CFS Coordinator | Chief Officer National CFS Governance Group National CFS Coordinator HBS Finance Primary Care Finance
40 | 3c | Day to Day Performance & Issue Management | Regular routine meetings with suppliers to discuss performance/ customer feedback/ operational issues and improvements for both sides if required. Template available. The customer is the CHO. There is a working relationship between the supplier and prescriber. All operational issues should be dealt with at this level. Any issues for escalation should be directed to procurement for logging and resolution. | CHO CFS Coordinator & HBS procurement for some parts | Chief Officer | National CFS Governance Group National CFS Coordinator HBS Procurement | Chief Officer National CFS Governance Group HBS Procurement HBS Finance Primary Care Finance
41 | 3d | KPI monitoring & feedback to “sourcing” | Regular capturing of KPI data e.g. on time / full load deliveries, response times to call outs/first time fixes, collated and returned to Sourcing Organisation operations team for monitoring at national level | CHO CFS Coordinator & HBS Procurement for some parts | Head of Service | Head of Service National CFS Coordinator | National CFS Governance Group Chief Officer National CFS Coordinator HBS Finance Primary Care Finance
50 | 3e | Recording compliance to policy & savings | Reporting on “contract leakage” (situations where framework contractors not used / unable to supply) with reasons, reporting on volumes purchased X price v previous period to calculate savings | CHO CFS Coordinator & HBS Procurement for some parts | CHO CFS Management Group | CHO CFS Management Group National CFS Coordinator HBS Procurement | Chief Officer National CFS Governance Group HBS Procurement HBS Finance Primary Care Finance
51 | 3f | Periodic Contract Performance Review | Formal, typically annual review of contractor performance against KPIs, customer satisfaction. Detail and depth will vary greatly depending upon strategic importance of contract to customer. Template available | CHO CFS Management Group | Chief Officer | Supplier HBS Procurement National CFS Coordinator | Chief Officer National CFS Governance Group HBS Procurement HBS Finance
52 | 3g | Supplier Relationship Management | On-going engagement and management of suppliers by the Sourcing Organisation at Framework level to drive improvements in VFM/ innovation / mutual cost reduction, transactional efficiency etc. | HBS Procurement | Head of Procurement | National CFS Governance Group ND Community Operations HBS Finance | National CFS Governance Group ND Community Operations HBS Finance Chief Officers
53 | 3h | Dispute escalation & resolution, change control, contract extensions, termination | Contractual matters that go beyond day to day issues outlined in 3c above that should be managed at framework level. (May be escalation from “C” and “F”). Includes contract extensions and decisions to terminate | HBS Procurement | Head of Procurement | ND Community Operations Chief Officers National CFS Governance Group HBS Finance | ND Community Operations Chief Officers National CFS Governance Group HBS Finance
54
60
61
65
66
67
68
69
80