## Sheet1
Appendix 2
Example Contract Implementation Plan
No. | Action | Responsible | Completion Date | Dependencies | Risks | Status | Notes
1 | Approval of Implementation Plan |  |  |  |  | completed
2 | Identify implementation Steering Group and goverance process |  |  |  |  | completed
Product Contract
3 | Finalise list of products for new contract |  |  |  |  | completed
4 | Agree pack sizes of products for new contract |  |  |  |  | in progress
5 | Agree sample packs for service user and prescriber |  |  | previous task completion |  | Not Started
6 | Draft National Order Form and Clinical Guidelines |  |  |  | timeline | in progress | other tasks depend on this
7 | Approve National Order From and Clinical Guidelines |  |  |  |  | Not Started
8 | Identify lead HSE contact person for SLAs (Product) |  |  | Approval/Availability | Timeline | Not Started | necessary for signing contract
9 | Agree Service Level Agreements (Product) |  |  |  | Timeline | Not Started
10 | Sign Service Level Agreements (Product) |  |  | outcome court proceedings | dependencies | Not Started
11 | Approve message for existing product advisers |  |  |  | Timeline | overdue | opportunity for same passed
12 | Review Operational Procedures and SOPs |  |  |  |  | Not Started
13 | Approve Operational Procedures and SOPs |  |  |  |  | Not Started
14 | Review training pack (online tutorials and training materials) |  |  |  | Timeline | Not Started
15 | Approve Training Pack |  |  |  |  | Not Started
16 | Agree Management of Stock policy |  |  |  |  | Not Started
17 | Review and Approve Supplier Implemenation Plan |  |  |  |  | Not Started
18 | Draft list and sequencing of performance management reports |  |  |  |  | Not Started | proposed mgt. Reports to be sent to group
Finance
19 | Identify address for payment of single monthly payment file |  |  |  |  | completed
20 | Identify components for single monthly payment file |  |  |  | Timeline | in progress
21 | Map process for validation and apportionment of single monthly payment file |  |  |  |  | in progress
22 | Test process for validation and apportionment of single monthly payment file |  |  | operational stakeholder involvement |  | Not Started | Active operational stakeholder engagement required
25 | Roll-out process for validation and apportionment of single monthly payment file |  |  |  |  | Not Started
26 | Draft list and sequence of financial management reports |  |  |  |  | Not Started
27 | Approve list and sequence of management reports |  |  |  |  | Not Started
IT
29 | Transfer Implementation Plan into Project Vision
30 | Draft IT non-disclosure agreement |  |  |  |  | in progress
31 | Transfer and clean down data files sent to HSE |  |  |  | Timeline | Not Started | Required for client data validation by CHO's
32 | Request regular updates re data |  |  |  | Timeline | Not Started
33 | Update system as appropriate |  |  | Information/resource availability | Timeline | Not Started
34 | Review and Approve Distributor IT model |  |  | Information/resource availability | Timeline | Not Started
Delivery Contract
35 | Review SOPs for Customer Support |  |  |  | Timeline | Not Started
36 | Approve SOPs for Customer Support |  |  | previous task completion
37 | Identify delivery locations/schedules |  |  |  |  | in progress
38 | Review SOPs for delivery |  |  |  | Timeline | Not Started
39 | Approve SOPs for delivery |  |  | previous task completion
40 | Review location for storage and process for distribution |  |  |  |  | Not Started
41 | Identify checklist for assurance of management of fleet and drivers |  |  |  | Timeline | Not Started | Part of ongoing contract management
42 | Quality assure management of fleet and drivers |  |  |  | Timeline | Not Started | as previous
43 | Agree Service Level Agreements (Delivery) |  |  |  | Timeline | Not Started
44 | Sign Service Level Agreements (Delivery) |  |  |  | Timeline | Not Started
Clinical Guidelines
45 | Finalise Paediatric Guidance Document |  |  |  |  | in progress
46 | Approval of Paediatric Guidance Document |  |  | previous task completion |  | Not Started
47 | Draft Adult Guidance Document |  |  |  | Timeline | Not Started
48 | Approval of Adult Guidance Document |  |  | previous task completion |  | Not Started
49 | Develop information leaflets |  |  |  |  | in progress
50 | Develop standardised training pack |  |  |  |  | in progress
Communication
51 | Draft SIG Communciation Plan (Identifying What, Who, When) |  |  |  |  | completed
52 | Review and Sign -off SIG Communciation Plan |  |  |  | Timeline | in progress
53 | Draft DOH briefing |  |  |  |  | in progress
54 | Review and Sign-off DOH Briefing |  |  |  | Timeline
55 | Draft FAQ's |  |  |  |  | completed
56 | Review and Sign-off FAQ's |  |  |  | Timeline
CHO
57 | New process for CHO 3rd party product approval to be developed in individual CHO's |  |  |  | Timeline |  | Each CHO will need to identify own process and considerable risk of adverse publicity if not achieved
58 | Identification of existing 3rd party product users | [5 empty] | will be possible to use existing data sources in some CHO's
59 | Communciation with Cos/HOS outlined in Communication Plan |  |  | Input from all members | Timeline | in progress
60 | Information Workshops to be delivered in each CHO |  |  |  | Timeline |  | need to determine number, scope and content of these workshops