## Sheet1
Implementation Readiness Issues
Work Stream:
Contract:
Impact areas | Description of Impact | what needs to happen/planned now to reduce impact | what needs to happen/planned post contract | Potential monitoring needs post contract
Impact analysis of Contract change to service
new products: increased choice and improved technology with some contract | delay in awarding contract | Suppliers submitted implementation and structured Education Plan tailored for Staff and service users, roll out of same should be discussed with suppliers at contract finalisation and signing stage. |  | Clinical expert advisory group if any issue with new products. Need clarity on this process
new business process | new Order form and IT system | Trialling, Finalise and Agree new Order form and IT system | monitoring and compliance
roles & responsibilities | where there is a large scale of change for service | Where significant change is involved an implementation team is identified to support the pre and post contract requirements for a six to nine month period to support the transition and to manage communications, training design and development for patients and frontline practitioners in order to adapt to new business processes and products safely and effectively. This will not be a requirement for all of the work streams. | identify members of the implementation team including finance, procurement, logistics, and service members.
changeover lead in time
Legal & Regulatory Issues
scale up | certain contracts having a significant and high risk scale of change affecting patients and frontline practitioners
Impact analysis of Contract change to service user
new products | extended range of products and improved technology
new order/delivery system | change in quality of service to clients | address impact on service to clients. Communicate with, and support clients to manage changes and ensure quality of the service.
installation
support service available | change in support service | ensure adequate communication off, and access to support service
Impact analysis of Contract change to HSE staff
change to clinical practice , if yes what is impact on clinicians current practice | Prescribers, Nurses, HCP's, and Appliance officers affected by changes to clinical proactive | New national guidelines- undertake information sessions and education programme for dissemination and implementation of same. Prescribers-will need to have information on new products provided by supplier and refreshers on all products when required. Nurses/ HCP- will need full training on any change to clinical practice ie assessment and any on new products and refreshers on all products when required. Appliance officers- New order forms to be trialled and implemented.
new products / ordering process | new products and new order form | identify training requirements for clinicians. ensure robust IT system in place to accommodate same
new prescribing guidelines / SOPS | timelines for the national prescribing standards delayed | information sessions and training programme
new business process | staff awareness of same
roles & responsibilities | no identified CFS project point of contact at CHO level Logistics staff re-configured | decision needed on local contract management. Establish local implementation team with roles and responsibilities of service ,logistics, and procurement staff well defined and clarified | CFS Lead required in each CHO
Training plan
Identify training needs for prescribers/ business process staff | training and online training required for a number of the work streams to support frontline practitioners in adopting the new clinical standards and guidelines. | plan out in more detail and needs to be time lined in relation to contract start dates so that the training materials and online portals/facilities are in place. | deliver as relevant through local CNMEs
design programme |  | Prescribers-will need to have information/functionality on new products provided by supplier and refreshers on all products when required. Nurses/HCP- will need full training on any change to clinical practice ie assessment and any on new products and refreshers on all products when required. Appliance officers- New order forms to be trialled and implemented.
ICT skills for specific staff | Contracts require an assets management and a patient management system to be put in place. Will it be ECRI-AIMS plus or another system? | Decision on ICT and asset and patient management systems to be used. Availability of and training required in same.
Legal & Regulatory Issues
Procurement challenges | plan out each of the tenders across the six work streams in order to map out what needs to happen from now to going live with contracts and post contract?
Compliance with NFR
SLA | signing of SLA
Q&R standards
HIQA/ professional bodies
Financial & Business Issues
Implementation of a standardised national approach to coding arrangements for Aids and Appliances | Setting up/closing and re-pointing codes. Potential work load involved in implementing the changes and the capabilities of current IT systems to action the same. | Each CHO area finance team will need to identify the various tasks involved in implementing any proposed national cost elements | Ensure each new product has it's own product code/materials master code and any new products are mapped correctly | Each CHO area finance team will be responsible for cost element arrangements. Transition to IFMS will need to incorporate agreed coding arrangements.
Business process proofing / testing
Procurement challenges | Need to have product catalogue consistently defined across all procurement systems. If purchasing is completed on manual orders there will be no means to automatically code items to the required GL code. Retrieval of purchasing information will not easily be possible if manual order systems are in place (ie manual order books) | Examine the possibility of putting products through the National Logistics system for areas which do not have access to SAP materials management module
Good industry standards | as per contract
GDPR | compliance | built into design of relevant forms/sops
Operational monitoring of contract | If contracts are not monitored formally there is a significant risk of value being lost through either supplier non-performance or the business not adhering to its own business process | Agree mechanism in advance for monitoring of contracts including the establishment of a KPI set. This should form part of contract negotiation process. A possible model is representative of the services working in a process led by procurement CRMs | Agree standard set of KPIs to manage the contract and ensure VFM Being achieved | Run the reports regularly and work through the CRM led process for engagement with the business and the supplier.
Communications
Key messages to describe scale of change to patient, service , staff | Ensure key changes are identified and develop key messages that are clear and capture the change for staff, patient and service. Signpost available resources | Each group to identify key changes Group input to identify and develop any necessary supporting resources Timelines agreed per group to ensure communications items and any supporting resources are developed and available when needed | Dissemination of communications as per group's communications plan | ensure that the Procurement Evaluation Groups
FAQ / plan for each stakeholder group | as above | communications planning and preparation required in advance of changes being implemented; timely input and sign-off on plans and items required by each group | communications to issue as planned, two-way acknowledgements required internally to ensure this | (PEGs) evolve into Clinical Expert Groups
prepare for information sessions | information sessions required for CHO staff to capture required changes to practice and process | CFS governance - identify opportunities for combined approach: e.g. similar financial processes identified across three groups - could be delivered as combined info session plan sessions and identify necessary resources input required from finance, procurement to highlight changes for operational staff | deliver info sessions | to review product lists and monitor contract
DOH / National Director/ briefing | input required from each group and sign-off required | prepare and sign-off briefings submit as per governance structure - with confirmation that all relevant parties have received the brief and have no further requests for info |  | implementation post contract on a quarterly basis thereafter.
ICT/ data management | no current ICT application in place to support new or existing contracts with vendors. | decision required if adopting ECRI-AIMS SYSTEM
Patient /product data held | lack of patient data and clear process for housing data currently | need to map out where current patient and product data is held and managed and agree who oversees and manages future national data across the six work stream areas | migration of service user data | BY WHOM?
Product / patient database register | patient product recall/alert | patient registry required | monitoring of registry
Migration of service user data
ICT skills for specific staff | If ECRI AIMS system adopted then appliance officers/ admin staff will require training.
Asset management
ECRI AIMS | CFS technical specifications versus ECRI AIMs System. ECRI AIMS is compatible for asset tracking mgt and product recall and would be preferred option as all that is required is additional license to extend the system. It is not sufficient for recycling or patient mgt profile which CFS requires. However there may an opportunity to interface ECRI AIMS and PCMS.
training/ instruction manual required | If ECRI AIMS system adopted then appliance officers/LHO admin staff will require training.